## Instructions
Yearly Project Plan Template (Sample)
How to use:
1) Projects sheet: define each project's Start Month and End Month (Jan–Dec). StartIdx/EndIdx/Duration are calculated.
2) Allocations sheet: add one row per Developer–Project assignment. Choose Developer and Project from dropdowns.
3) Enter monthly effort as a fraction (0.00 to 1.00). You can only enter effort within the project's active months.
• Outside active months: cell must be blank (validated) and is shaded grey.
4) Summary sheet: project totals by month + developer utilization by month (cells turn red if utilization is <1 or >1).
Tip: Add more developers on the Lists sheet and more projects on the Projects sheet—dropdowns update automatically.

## Lists
Developers | Months |  |  | BlendRate | 500 | Mandays
Developer | Jan | DailyRate | RateRatio (Rate/Blend) | Mandays | 21 | 20
Dev 1 | Feb | 500 |  |  |  | 20
Dev 2 | Mar | 600 |  |  |  | 20
| Apr |  |  |  |  | 20
| May |  |  |  |  | 20
| Jun |  |  |  |  | 20
| Jul |  |  |  |  | 20
| Aug |  |  |  |  | 20
| Sep |  |  |  |  | 20
| Oct |  |  |  |  | 20
| Nov |  |  |  |  | 20
| Dec |  |  |  |  | 20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20

## Projects
Project | Start Month | End Month | StartIdx | EndIdx | Duration (months) | Notes
Project A | Jan | Mar |  |  |  | Example 3-month project
Project B | Jan | May |  |  |  | Example 5-month project
Project C | Jan | Feb |  |  |  | Example 2-month project
Project D | Jul | Sep
Project E | Oct | Dec
Project F | Aug | Nov

## Allocations
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Developer | Project | Start Month | End Month | StartIdx | EndIdx | Row Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | DevRate | Feb Cost | Mar Cost | Apr Cost | May Cost | Jun Cost | Jul Cost | Aug Cost | Sep Cost | Oct Cost | Nov Cost | Dec Cost
Dev 1 | Project A | [5 empty] | 1: 0.5; 2: 0.25; 3: 0.25
Dev 1 | Project B | [5 empty] | 1: 0.25; 2: 0.25; 3: 0.25; 4: 0.5; 5: 0.5
Dev 2 | Project A | [5 empty] | 2: 0.5; 3: 0.5
Dev 2 | Project C | [5 empty] | 1: 0.5; 2: 0.5
Dev 1 | Project D | Jul | Sep |  |  |  | 7: 0.5; 8: 0.75; 9: 0.5
Dev 1 | Project F | Aug | Nov |  |  |  | 8: 0.5; 9: 0.5; 10: 0.25; 11: 0.5
Dev 2 | Project E | Oct | Dec |  |  |  | 10: 0.75; 11: 0.5; 12: 1
Dev 2 | Project F | Aug | Nov |  |  |  | 8: 0.25; 9: 0.25; 10: 0.5; 11: 0.75

## Summary
Project summary (effort by month) | [13 empty] | BlendRate
Mandays
Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
TOTAL (all projects)
Project budget (SGD) - Effort x Mandays x DevRate
Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
TOTAL (all projects)
TOTAL (all projects)
Developer budget (SGD) - Utilization x Mandays x DevRate
Developer | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
TOTAL (all projects)
TOTAL (all projects)