## Instructions
Yearly Project Plan Template (Sample)
How to use:
1) Projects sheet: define each project's Start Month and End Month (Jan–Dec). StartIdx/EndIdx/Duration are calculated.
2) Allocations sheet: add one row per Developer–Project assignment. Choose Developer and Project from dropdowns.
3) Enter monthly effort as a fraction (0.00 to 1.00). You can only enter effort within the project's active months.
• Outside active months: cell must be blank (validated) and is shaded grey.
4) Summary sheet: project totals by month + developer utilization by month (cells turn red if utilization is <1 or >1).
Tip: Add more developers on the Lists sheet and more projects on the Projects sheet—dropdowns update automatically.

## Lists
Developers | Months
Dev 1 | Jan
Dev 2 | Feb
Dev 3 | Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec

## Projects
Project | Start Month | End Month | StartIdx | EndIdx | Duration (months) | Notes
Project A | Jan | Mar | 1 | 3 | 3 | Example 3-month project
Project B | Jan | May | 1 | 5 | 5 | Example 5-month project
Project C | Jan | Feb | 1 | 2 | 2 | Example 2-month project
Project D | Jul | Sep | 1 | 3 | 3
Project E | Oct | Dec | 1 | 3 | 3
Project F | Aug | Nov | 1 | 3 | 3

## Allocations
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Developer | Project | Start Month | End Month | StartIdx | EndIdx | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Dev 1 | Project A | Jan | Mar | 1 | 3 | 1: 0.5; 2: 0.25; 3: 0.25
Dev 1 | Project B | Jan | May | 1 | 5 | 1: 0.25; 2: 0.25; 3: 0.25; 4: 0.5; 5: 0.5
Dev 2 | Project A | Jan | Mar | 1 | 3 | 2: 0.5; 3: 0.5
Dev 2 | Project C | Jan | Feb | 1 | 2 | 1: 0.5; 2: 0.5
Dev 1 | Project D | Jul | Sep | 1 | 3 | 7: 0.5; 8: 0.75; 9: 0.5
Dev 1 | Project F | Aug | Nov | 1 | 3 | 8: 0.5; 9: 0.5; 10: 0.25; 11: 0.5
Dev 2 | Project E | Oct | Dec | 1 | 3 | 10: 0.75; 11: 0.5; 12: 1
Dev 2 | Project F | Aug | Nov | 1 | 3 | 8: 0.25; 9: 0.25; 10: 0.5; 11: 0.75

## Summary
Project summary (effort by month)
Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project A | 0.5 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project B | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project C | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project D | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.75 | 0.5 | 0 | 0 | 0
Project E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.5 | 1
Project F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.75 | 0.75 | 1.25 | 0
TOTAL (all projects) | 1.25 | 1.5 | 1 | 0.5 | 0.5 | 0 | 0.5 | 1.5 | 1.25 | 1.5 | 1.75 | 1
Developer utilization (total effort by month)
Developer | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Dev 1 | 0.75 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 1.25 | 1 | 0.25 | 0.5 | 0
Dev 2 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 1.25 | 1.25 | 1
Dev 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0